## All
ID	Name	Component	Version	Type	Status	Assigned	Grouping	Reaction	Jesse Comment	Jim Comment	John Comment
684	Plugin Package Swap for Toolset Menus	General	2.0.15	Improvement	New	Jesse	Toolset	Close	Becomes irrelevant with the new menu code.	Agreed.
1749	Deprecating plugins	Plugins	2.4.3	Feature Request	New	Jesse	Toolset	Close	Filtering will be part of the toolset redesign.	Should rename this to reflect change of design.
1834	Job History Panel	Graphical Client	2.4.5	Feature Request	New	John	JobNavigation	Discuss	This can happen independently of any of the other queue features	Agreed. It think this is a good feature by itself regardless of what we decide to do with the other queue UI enhancements.	I like this one too.
1855	Template builder suggestion: TemplateProp annotation	Node Builders	2.4.5	Feature Request	New	Jesse	-	Discuss	Not sure what the best solution to this problem is. So we need to scrum-up on this.	Agree that I have no idea how to do this though...
1754	UI bug: text field isn't marked as dirty until you hit Enter	Graphical Client	2.4.3	Annoyance	New	John	-	Discuss	This would be really good to have, I think, but we need to figure out a sane way to do it.	Added the DocumentListner idea to post.
1397	Per-Node Archiving/Offlining Properties	General	2.3.15	Feature Request	Active	Jim	-	Discuss	When we introduce node typing for data locality, this seems to be a logical extension to that.	Not really. There would be different criteria. I don't think this is a high priority and it can wait until someone actually starts wanting to use the offline/archive features in a more sophisticated way.
1332	optional display of full/partial node name in node viewer	Graphical Client	2.3.11	Improvement	New	-	-	Discuss	We need to figure out if we want to do this. pipeline 3 negates the need for this feature	John could add very basic support for this when he does the NodeStyles feature.
1694	Improvement: NukeSubstComp Action	Plugins	2.4.3	Improvement	New	-	-	Defer	Until we have another hardcore Nuke studio.	Agreed.
1658	Way to view StdErr, StdOut of Editors	Graphical Client	2.4.3	Feature Request	New	-	-	Defer	Since I'm the only one who seems to care, we can just let it go for now.	Agreed. Would be useful for debugging editors, but not a real high priority since you can see the output in the LogHistory panel now.
802	Update the Manual	Docs	2.1.2	Improvement	New	All	-	Soon	Wiki = new docs
582	Changing Toolset needs to invalidate Action/Editor	General	2.0.7	Improvement	New	Jesse	Toolset	Open	This is a massive change, but I feel like it has to happen.	Agreed, but only as a warning not blanking the Action/Editor fields.
1705	Exclusive is not always exclusive in Toolsets	Java API	2.4.3	Improvement	New	Jesse	Toolset	Open	Need to deal with this, I think	Ok, but we need to discuss this before you implement it.
1883	Default Editor listing	Graphical Client	2.4.5	Improvement	New	Jesse	Toolset	Open	Will solveit.	Just need a way to assign one of your Toolset2 editor menus to the panel.
975	Clean Unused Toolsets	Server Daemons	2.1.9	Feature Request	Active	Jesse	Toolset	Open	The toolset conversion tool will deal with this. Having underDevelopment toolsets will hopefully cure the rest.	Agreed.
973	Add ArchType for Toolsets	General	2.1.9	Feature Request	New	Jesse	Toolset	Open	Working on this now. Sigh.	Agreed.
1837	Scheduling: actions request how many slots they want	Server Daemons	2.4.5	Feature Request	Active	Jesse	Queue	Soon	This can be done before the main queue overhaul and would be wicked	Agreed.
1684	Multiple Key Choosers per Key	Plugins	2.4.3	Feature Request	New	Jesse	Queue	Soon	In my spare time.	Disagree. I think this would be fairly simple to add and be of great benefit. Maybe team up with John on the UI bits.
1707	auto-disable job manager	Server Daemons	2.4.3	Feature Request	Active	Jesse	Queue	Defer	Probably be done after the main queue redesign.	Maybe write an example QueueExt plugin as a temporary solution?
1318	rendering exclusively on machines	Server Daemons	2.3.8	Feature Request	New	Jesse	Queue	Defer	This will be considered in the great queue redesign.	Agreed.
708	Flag to avoid run-up time	General	2.0.16	Improvement	Active	Jesse	Queue	Defer	If I'm modifying the queue, I might as well modify this too.	Agreed.
1613	Job Dispatch Revisited	Server Daemons	2.4.2	Feature Request	New	Jesse	Queue	Defer	This is the heart of the queue redesign	Agreed.
275	Distributed Jobs	General	1.9.3	Feature Request	Active	Jesse	Queue	Defer	As part of the Queue Redesign, we should be able to support Distributed Jobs	Agreed, really should be part of 1613.
1836	More Detailed Reservations	General	2.4.5	Feature Request	New	Jesse	Queue	Defer	Slots will become the basic unit of commerce in the queue redesign.	Agreed.
951	Redesign of Package Layout	Java API	2.1.9	Feature Request	New	Jesse	Pipeline 3	Defer	We'll break everything as part of the Pipeline 3 upgrade.	Massive refactoring can wait.
1121	Job Execution Details for Each Attempt	General	2.3.2	Feature Request	New	Jesse	JobExecution	Soon	Allowing jobs to rerun would be great.	Independent of dispatcher overhaul, should be done sooner.
97	Job Output Parsing: Monitor/Validator Plugins	Java API	2.4.5	Feature Request	Active	Jesse	JobExecution	Soon	Part of the queue overhaul. This could also be done separately, but who has the time?	Independent of dispatcher overhaul, should be done sooner.
1401	Add parameters to Editors	Plugins	2.3.15	Feature Request	New	Jesse	EditorParams	Defer	Yeah. this would be great. Whenever I get to it. Hah.	Agreed.
1787	Shotgun tasks created by Pipeline include the asset name	Plugins	2.4.5	Annoyance	New	Jesse	-	Open	Just need to merge some code into the trunk. I'll do this ASAP	Agreed.
1932	Template Builder: Clone files problem	Node Builders	2.4.6	Annoyance	New	Jesse	-	Open
1936	Releasing View	Graphical Client	2.4.6	Defect	New	Jesse	-	Open
1925	Template Touch setting fails on conform	Node Builders	2.4.6	Defect	New	Jesse	-	Test
1794	Node modified, but no staleness	Node Builders	2.4.4	Defect	New	Jesse	-	Test	No idea how to reproduce this right now.	No idea. Hopefully it will go away when I overhauld the status code.
1929	Need a CustomEntityType on Task* annotations	Plugins	2.4.6	Feature Request	New	Jesse	-	Trivial
1811	Builder AoE Modes	Node Builders	2.4.5	Feature Request	New	Jesse	-	ASAP	Because it solves lots of problems.	Agreed.
1844	Template builder suggestion: TemplateExternal annotation	Node Builders	2.4.5	Feature Request	New	Jesse	-	ASAP	Because I told lumiere I'd do it
1848	Hardware Groups Bug	Graphical Client	2.4.5	Severe Defect	New	Jesse	-	ASAP	Shouldn't be too hard to fix once I figure out what it is.	This is definitely caused by removing all of the HardwareKeys used by a HardwareGroup. Bad PR when it breaks and jams everything up, so should be ASAP
1917	Unique order on multi-source nodes fails with templates	Plugins	2.4.6	Defect	New	Jesse	-	ASAP	Add a flag to CatFiles	Agreed.
1599	Synch and Unify nodes for the Task System	Java API	2.4.2	Feature Request	New	Jesse	-	Soon	The entire task system needs a quick update. I should do that sooner rather than later. Sigh.	Read my last post in 1596. Looks like we need to first agree on the approach to take here. Mine does not require Sync and Unify nodes and I think is both simpler and better. You may disagree.
1571	Annotation Exceptions with Clone Due to Permissions	General	2.4.1	Feature Request	New	Jesse	-	Soon	We really need to address this at some point.	Renamed this bug.
1495	KeyChooser Plugin Updates	Server Daemons	2.4.1	Defect	New	Jesse	-	Soon	Really should fix this.	Agreed and soon.
631	Alternative Job Submission Order	General	2.0.9	Improvement	New	Jesse	-	Soon	Great idea and I should do it when I finish toolsets.	Agreed.
1417	Reorganize CompBuild Action Parameters	Plugins	2.3.15	Improvement	New	Jesse	-	Soon	This should be done.	Agreed, but not that high priority.
1536	Add Frame Options to Queue Job Special	Graphical Client	2.4.1	Feature Request	New	Jesse	-	Soon	As soon as Toolsets are done, I should do this.	Can't see how this is a pressing issue.
1563	TaskToolUtils.findUpstreamNodes() is Slow!	Java API	2.4.1	Improvement	New	Jesse	-	Soon	This will be eliminated by the Task redesign anyway. But working code exists in TemplateBuilder, so I should just copy/paste it.	Agreed.
1626	query plugin mgr for plugins that are not underdevelopment	Node Builders	2.4.3	Feature Request	New	Jesse	-	Soon	Be nice when it is there.	Agreed.
1614	A JobGroupID field in a QueueJob	Java API	2.4.2	Improvement	New	Jesse	-	Soon	Do this soon.	Agreed.
1323	System Load on Windows Inconsistent with Unix Load	Server Daemons	2.3.13	Defect	New	Jesse	-	Soon	Need to do something with this to make it better	Agreed.
1918	Default host selection mecanism for jobs	General	2.4.6	Improvement	New	Jesse	-	Soon	Becomes obsolete with the queue redesign, but would be easy to do in the mean time.	Added some ideas to post about implementation.
1882	Builder improvement: rerun, and autofill with last params	Node Builders	2.4.5	Feature Request	New	Jesse	-	Soon	Not easy, but I told lumiere I'd do it
1939	Template: Adaptive Copy Setting.	Node Builders	2.4.6	Feature Request	New	Jesse	-	Soon
1014	Adobe CS2 Export Action Plugins	Plugins	2.4.5	Feature Request	New	Jesse	-	Defer	Not even sure if Photoshop accepts command-line scripts correctly.
1319	Needs docs for Eclipse pipeline-local setup	Docs	2.3.12	Improvement	New	Jesse	-	Defer	Give me a wiki and I'll give you docs	Agreed.
1835	Job Duration Prediction	Server Daemons	2.4.5	Feature Request	New	Jesse	-	Defer	This needs to wait till the Database manager is a reality, so that data mining becomes easy	Agreed.
1931	Example Java Task Tracker	General	2.4.6	Feature Request	New	Jesse	-	Defer
1297	Builder Man Pages	Docs	2.3.11	Feature Request	New	Jesse	-	Defer	Since we don't have any new builders, it doesn't make sense to do docs for the outdated ones.	I'll let it slide...
703	Queue Distribution Based on Local Caching	General	2.0.16	Improvement	Active	Jesse	-	Defer	We need to implement local caching first (which I'm not doing). Once that is done, I can do this.	Need to reevaluate. Not sure local caching is really all that important with current hardware.
1734	Windows Service Should Run JVM as a Separate Process	Server Daemons	2.4.3	Improvement	New	Jim	WinJobMgr	ASAP	Because Windows should work.	Agreed and as much as I dread it, it needs to be done.
1025	Remote Windows Job Server Shutdown	Server Daemons	2.2.1	Defect	New	Jim	WinJobMgr	ASAP	Be really nice to actually be able to stop jobmgrs on Windows	Would be solved by 1025. I hope.
1896	Frames are not always copied from target directory	Server Daemons	2.4.5	Defect	New	Jim	WinJobMgr	Soon	Leads to really bad behavior with Windows JobManagers	Agreed.
1736	QueueMgr doesn't update job count correctly after disconnect	Server Daemons	2.4.3	Severe Defect	Active	Jim	Windows	Test	Not sure we know enough about this to really effectively tackle it. Also it appears to be Windows-only, so it can wait.	This is bad enough that we can't ignore it, but we don't know what is causing it either.
1421	Symlinks to Target are not relative	Server Daemons	2.3.15	Defect	New	Jim	Windows	Soon	This becomes a priority when we have a heavy windows customer	Should be fixed sooner.
1893	Better status reporting for jobs that silently fail	Graphical Client	2.4.5	Improvement	New	Jim	VC Speed	ASAP	Very simple. but huge win.	Free as part of JobMgr checksum generation.
1854	Reducing fileserver traffic/checkin time: Move vs. copy	Server Daemons	2.4.5	Improvement	New	Jim	VC Speed	ASAP	Best feature ever.	Absolutely!
1138	Checksum Caching	Server Daemons	2.4.5	Improvement	Active	Jim	VC Speed	Soon	Speed upgrades are good.	Part of VC Speed improvements.
1892	Renumber Does not Propigate Staleness correctly.	Java API	2.4.5	Severe Defect	New	Jim	Status Overhaul	ASAP		Must fix soon.
1124	Database Manager	General	2.3.2	Feature Request	New	Jim	SQL	Defer	Maybe we do this sooner, since it would allow for a lot of cool stuff, but I don't really see it having precedence	Agreed.
1792	locking nodes associated with running jobs	General	2.4.3	Annoyance	New	Jim	QueuedChecks	ASAP	Actually pretty easy to break jobs this way.	Agreed.
1395	overly restrictive prohibitions on checkout	General	2.3.14	Annoyance	Active	Jim	QueuedChecks	Soon	Yeah, it is annoying but people can deal.	Same code as in 1792, should do together.
966	Improved Node Property Job Checks	Java API	2.1.9	Improvement	New	Jim	QueuedChecks	Soon	Good idea to make Pipeline more robust.
366	PLS Frame Increment Incorrect	General	1.9.15	Annoyance	New	Jim	PLS	Trivial	Should be a fairly easy fix	Agreed.
1481	make pls output in the "standard pipeline format"	General	2.4.1	Improvement	Active	Jim	PLS	Defer	I read the bug report on this. I think Jim was talking to himself. I have no idea what it means.	No one appears to use pls, but this but should be fixed at some point.
1477	Replace Jython?	Scripting Client	2.4.1	Improvement	Active	Jim	PLPYTHON	Defer	In your spare time.	Agreed.
1341	NodeEnvironment plugin type	Plugins	2.3.13	Feature Request	New	Jim	Pipeline 3	Defer	I think a majority of what we want to do here can be incorporated into Workflow graphs in Pipeline 3.	Agreed.
445	Unequal Frame Length Secondary Sequences	General	1.9.21	Feature Request	Defer	Jim	Pipeline 3	Defer	Goes with 1169 to Pipeline 3	Agreed.
478	Parameter Nodes and Linking Parameters	General	1.9.21	Feature Request	Active	Jim	Pipeline 3	Defer	Not necessary in Pipeline 2. Fits perfectly into the Pipeline 3 metaphor.	Agreed.
1169	Node Groups instead of Secondary Sequences	General	2.3.4	Feature Request	New	Jim	Pipeline 3	Defer	Yeah, this would be good, but it honest requires enough changes to how Pipeline works that rewriting everything twice would suck.	Agreed.
774	Arbitrary Frames	General	2.1.1	Feature Request	New	Jim	Pipeline 3	Defer	Yeah, it would be great. But no current customers want it and this makes secondary sequences hell, so lets leave it till Pipeline 3.	Agreed.
109	Node Thumbnails	Graphical Client	1.8.2	Feature Request	Defer	Jim	Pipeline 3	Defer	Thumbnailing becomes part of Tasks in Pipeline 3	Agreed.
367	Remote Clients / Secondary Servers	General	1.9.15	Feature Request	Active	Jim	MultiSite	ASAP	Part of the MultiSite feature group.	Agreed.
698	Node Data Locality	General	2.0.16	Feature Request	New	Jim	MultiSite	Soon	Could be part of the MultiSite stuff?	Sort of independent, but would touch much of the same code. Might as well deal with it at the same time.
706	Redundant Master Servers	Server Daemons	2.0.16	Feature Request	Active	Jim	MultiSite	Soon	We really don't need this, though we should consider it when adding multiple site stuff, since we might get it for almost free.	Should be done as part of MultiSite.
1335	Access to scratch files across the network	Server Daemons	2.3.13	Feature Request	New	Jim	JobViewing	Soon	Really, really, really useful idea.	Agreed.
719	Use Editor to View Job Logs	Graphical Client	2.0.17	Improvement	New	Jim	JobViewing	Soon	Quite useful and could be combined with the Scratch Dir viewing as well	Agreed.
769	Clone with Linked History	Java API	2.0.17	Feature Request	New	Jim	Branching	Defer	Great idea. Who has the time?	Should be done with 1108.
895	Node History Dialog	Graphical Client	2.1.7	Feature Request	New	Jim	Branching	Defer	Could be done without the branching code, but I don't see anyone screaming for this.	Should be done with 1108, 769.
1108	Node Merge	General	2.3.1	Feature Request	New	Jim	Branching	Defer	Awesome idea, do we really need it? Is it Pipeline 3 compliant?	Doesn't matter, nothing from Pipeline2 will be. Should be done with 769.
573	Intermediate Nodes	General	2.0.6	Feature Request	New	Jim	-	Open	Currently being worked on.	Waiting on Status improvements first.
1765	plpython enhancement	Scripting Client	2.4.4	Improvement	New	Jim	-	Test	We should figure out what we want to do about this and then either On Hold it or do it	Not entirely sure we should reject, need to test some things first.
1643	Offlining/Archive appears to lockup Pipeline	General	2.4.3	Severe Defect	Active	Jim	-	Test	Haven't been able to reproduce this lately	We haven't really tried very hard to replicate it and it is a serious issue. We should investigate more soon.
1903	stdout/stderr doesn't appear in the Output or Errors dialogs	Graphical Client	2.4.6	Annoyance	New	Jim	-	Test	Not sure how to replicate it.	Me either.
1036	NukeBuild Action	Plugins	2.1.2	Feature Request	Active	Jim	-	Test	Isn't this done and working? Can you test it jim?
1640	Mac OpenGL performance issues	Graphical Client	2.4.3	Annoyance	New	Jim	-	Test	Is this still happening? Need confirmation from Kevin	Not sure.
1506	Add a LaunchPipe Python Helper	Java API	2.4.1	Improvement	Active	Jim	-	Test	This should be tested or removed from the code base.	I wrote it, so I'll look at it.
1716	Add ability to flush user cache in runtime	General	2.4.3	Feature Request	New	Jim	-	Trivial	How often is changing uids in the middle of production a problem?	Easy to do and has caused some problems before.
1605	plscript missing node locking ability	Scripting Client	2.4.2	Feature Request	New	Jim	-	Trivial	Lets not encourage people to use plscript	I disagree. As much as I hate doing it, we should keep plscript current.
1688	On Hold Locking to Same Version	Server Daemons	2.4.3	Improvement	New	Jim	-	Trivial	Easy enough.	Agreed.
1606	plscript missing "vouch" functionality	Scripting Client	2.4.2	Feature Request	New	Jim	-	Trivial	Lets not encourage people to use plscript	I disagree. As much as I hate doing it, we should keep plscript current.
996	Check for Unregistered Files During Intial CheckOut	Graphical Client	2.1.9	Feature Request	New	Jim	-	Trivial	Apparently Jim still cares	Yep. Renamed it too.
1142	Queue Database Backup	Server Daemons	2.2.3	Feature Request	New	Jim	-	ASAP	We should be doing complete backups	Agreed.
1798	Rename vouch is too aggressive	Java API	2.4.5	Severe Defect	Active	Jim	-	ASAP		Needs to be fixed soon.
1331	A New Type of Node which Represents a Directory	Java API	2.3.13	Feature Request	New	Jim	-	ASAP	Because there are a lot of really cool things we could do with this that we can't do right now.	Agreed.
1912	Add mv to NativeFileSys	Server Daemons	2.4.6	Feature Request	New	Jim	-	ASAP	Simple to do, but we need it.	Agreed. And John should change the PluginMgr code to use it too.
536	License Expiration Warnings	General	2.0.2	Improvement	New	Jim	-	ASAP	Remind people to give us money. This is a great idea.	50% implemented already. Just need to tweak it a bit.
1079	Node Instances	General	2.2.4	Feature Request	New	Jim	-	ASAP	Solves so many problems in Pipeline and can dramatically reduce disk usage. This is one feature we really need.	Ok, soon...
1339	Too much Job Group information sent	Graphical Client	2.3.13	Improvement	New	Jim	-	ASAP	This is a problem.	Disney evaluation makes this important.
1778	RealFlow Editor Support for Mac OS X and Windows	Plugins	2.4.3	Improvement	New	Jim	-	Soon	Sony seems to care	Agreed. Until someone asks for it...
1820	Add Failure Post-Operation Tasks to Server Extensions	Plugins	2.4.5	Improvement	New	Jim	-	Soon	This is a great idea.
1815	cannot unpack node bundles in windows	General	2.4.5	Defect	New	Jim	-	Soon	Shouldn't be that hard of a fix, but this should work	Agreed.
622	Node Browser: Hiding Old Projects	General	2.0.9	Feature Request	New	Jim	-	Soon	We should really do this.	This half UI and half backend. Possibly a John thing but likely still me.
739	Clock Monitoring	General	2.2.1	Feature Request	Active	Jim	-	Soon	Good idea, just need the time to do it.	Agreed.
1386	Long Operation Progress Meter	Java API	2.3.13	Feature Request	New	Jim	-	Soon	Not a bad idea at all.	Good idea but tricky
1629	Unlock/CheckOut Subvert Link Circularity Checks	Server Daemons	2.4.3	Defect	New	Jim	-	Soon	This is bad, but how often has this actually happened? Maybe once at Sony? So while it is a nasty bug, it also has an extremely low incidence as long as we	Its not actually that hard to do and it causes a major problem when it does happened that required manual database hacking to fix. This should be fixed soon..
1832	Collate Job Output	Graphical Client	2.4.5	Feature Request	New	Jim	-	Soon	This seems to be handled by different features	Nope. The part about marking Output/Error has having been read is important and fairly easy to do.
699	Skip Unchanged Flag	General	2.0.16	Feature Request	Active	Jim	-	Soon	Because Pipeline doesn't really work efficiently without it.	Agreed. Should be done after checksum improvements.
1562	Selection of Multiple Nodes from top of the directory	Graphical Client	2.4.1	Feature Request	New	Jim	-	Defer	Useful but not a priority	I don't know if I even care.
1677	Preserve Locations in NukeSubstComp	Plugins	2.4.2	Improvement	Active	Jim	-	Defer	Until we have another hardcore Nuke studio.	Agreed.
1662	Houdini Batch/Graphical License Selection	Plugins	2.4.3	Improvement	New	Jim	-	Defer	Really a much more tricky License Key issue	Agreed.
670	Frozen Finished Nodes should be check-in-able	General	2.0.14	Feature Request	New	Jim	-	Defer	Less necessary with the new task stuff, since modifiable nodes are rarely frozen.	Agreed.
518	HDiff Comparator Plugin	Plugins	2.0.0	Feature Request	New	Jim	-	Defer	No customers using Houdini	Very cool idea, but no demand.
1608	hfsMantra: adding ifd filtering functionality	Plugins	2.4.2	Feature Request	Active	Jim	-	Defer	No customers using Houdini	At the moment, should do this though.
962	Node Locks should be Interruptible	Server Daemons	2.1.9	Improvement	New	Jim	-	Defer	Useful, but there is other stuff way more important.	Agreed.
736	E-Mail Logging	Server Daemons	2.0.18	Feature Request	New	Jim	-	Defer	In your spare time.	Agreed.
1466	Nuke 5.0 Python Scripting Support	Plugins	2.4.1	Improvement	Active	Jim	-	Defer	Until we have another hardcore Nuke studio.	Agreed.

1908	Update plplugin to handle plugin resource information	Plugins	2.4.6	Improvement	New	John	-	Open	Needs to be checked-in	John?	This is done but decided to exclude in the releases while you away since it dealt with totally changing the interaction with plplugin.
1237	Release view matching pattern confirm dialog	Graphical Client	2.3.6	Improvement	New	John	-	Test	It doesn't do this already? I thought it did.	I thought so, need to test.
666	RegisterMap Tool Enhancement	Plugins	2.0.14	Improvement	New	John	-	Trivial	I apparently volunteered to fix this, but no one seems to care.	Looks easy and could be done by John.	I think I get this one.
1325	Refresh button in file browser	Graphical Client	2.3.13	Improvement	New	John	-	Trivial	Useful, but there is an easy work around so it can wait.	John can do this...	Understand the issue. What to use as the refresh button, or icon. Or we can piggyback on function keys, I think F5 is refresh for web browsers, would only work if we have focus on the Node Files Panel
1445	Standardize NodeNote UI	Plugins	2.3.15	Improvement	New	John	-	Trivial	Since I don't want to do it.	More of a John UI thing...	Understand the issue. Seems easy to do.
1374	Opening branch in node browser has strange behaviour	Graphical Client	2.3.14	Feature Request	Active	John	-	Trivial	There have been enough comments about this behavior that we should do something about it	Agreed.	Understand the issue. Seems easy to do.
632	Display of Long Node Names	Graphical Client	2.0.9	Improvement	New	John	-	Trivial	There are more pressing issues	John can do this...	Understand the issue. But not sure what the best solution is, I think the “...” might be best, but need something to provide more information if the user wants it.
1366	Queue Stats panel doesn't reset cursor	Graphical Client	2.3.13	Annoyance	New	John	-	Trivial	Not worth the time it would take to fix.	Perceived quality is all about the little things. Should fix now.	No mouse at the moment, but I think I understand the issue. Will review again later.
494	Multiple Evolve	General	1.9.21	Improvement	New	John	-	Trivial	Whenever you get around to it.	John can do this...	Understand the issue. Seems easy to do.
1669	Archive Tool Window	Graphical Client	2.4.3	Annoyance	New	John	-	Trivial	Just need to scale the table column to max length	Agreed. Do easy way.	I made a node with a ridiculously long name and if we were to scale the table column to the max length it would probably work if you have a 30 inch display. What if we made a a text field that you could slide to see more text by mouse dragging on the textfield to the left or right?
1441	Cloning Checked-In/Locked Nodes	General	2.3.15	Improvement	New	John	-	Trivial	When you get a chance.	John can do this... Maybe with our help on the backend.	This sounds handy to have. I guess the current way people would do this is to check out the node, then clone, then release the original node.
1579	using 'show node' to select multiple nodes	General	2.4.1	Feature Request	Active	John	-	Trivial	Simple fix.	Agreed.	Understand the issue. Seems easy to do.
1063	Show version comments in the checkout window	Graphical Client	2.2.3	Feature Request	New	John	-	Trivial	Real easy to do, improves user experience		There is a lot of space in the check out window, is that space ever used? If it is not, why not put the version comments in a text box there.
1594	beep!	Graphical Client	2.4.2	Annoyance	Active	John	-	Trivial	Because I don't care that much.	Easy to make this a preference.	I have heard the beeps on the Mac, when performing Apple key TAB to switch between apps the beep sound is made. Probably because the Apple key is used.
1078	Link Params values missing in Details for Locked Nodes	Graphical Client	2.2.4	Annoyance	Active	John	-	Trivial	Simple fix.	Agreed.	I see the issue, but it is a bit confusing as to which node it is linked to if I can not see the node details of the node linked. Seems easy enough to do.
1935	Release View	Graphical Client	2.4.6	Annoyance	New	John	-	Trivial
1825	node detail hints	Graphical Client	2.4.5	Annoyance	New	John	-	Trivial	This was going to be done a while ago, it is easy, and lumiere would like it.	John can do this...	Understand the issue. So the Preference is not being used until plui is restarted. Also the clipping issue needs to be fixed.
1701	problem with queuing multiple batches from the job viewer	Graphical Client	2.4.3	Annoyance	New	John	-	Trivial	Actually much more than an annoyance. This should get fixed quickly.	John can do this...
1689	Node Favourites Panel	General	2.4.3	Feature Request	New	John	Favorites	Soon	Brilliant idea.	Agreed.	This sounds like a handy feature. I like this one, not that I don't like all the other bugs and features, probably more accurate to say that I'm interested in working on this feature sooner than later.
1182	Selection History	Graphical Client	2.3.4	Feature Request	New	John	Favorites	Soon	Should be associated with the Node Favorites panel.	Agreed.	This is an interesting one too.
1607	Hardware Key Dial in Queue Stats	Graphical Client	2.4.2	Feature Request	New	John	Dials	Trivial	Very Easy	Subset of 987.	Understand the issue.
987	Generalize Queue Stats Panel	Graphical Client	2.1.9	Feature Request	New	John	Dials	Soon	Great idea and we should do it.	Agreed.	I like this, it makes it more like the Sun storage servers interface.
1752	machine note column in queue server	Graphical Client	2.4.3	Feature Request	New	John	Queue	Soon	Could do it now, but do I really need more on my plate. I can do this with the Queue overhaul	Is really a UI only thing, John can handle it sooner.	Sounds handy.
1639	Default Layout File empty/missing	General	2.4.3	Defect	Active	John	Layouts	Test	Should not be hard to fix	We know the symptoms but not the cause.	Understand the issue.
888	Save Layout as Site Default	Graphical Client	2.1.4	Improvement	Active	John	Layouts	Trivial	Easy enough to hack by hand.	Another easy one.	I like this one too.
1334	Reset Current destroys saved layouts	Graphical Client	2.3.13	Improvement	Active	John	Layouts	ASAP	This is not a good thing.	John can do this...	Understand the issue.
944	Save + Restore Window Bundles	Graphical Client	2.1.9	Improvement	New	John	Layouts	Soon	Would be cool, but isn't at all necessary. Pipeline 3 should negate the need for this.	Should do sooner than Pipeline3. Would be useful now.	This sounds handy.
1744	Save recent node operations between plui sessions	Graphical Client	2.4.3	Feature Request	New	John	Layouts	Defer	Good idea, but nothing we actually need to do.		I like this one too.
1167	Shared User Preferences	Graphical Client	2.3.5	Feature Request	New	John	Prefs	Defer	Would be great, lots of more important stuff	Could be done by John just as easily.
993	Custom Node Styles	Graphical Client	2.1.9	Feature Request	New	John	NodeStyles	Defer	Now this is an awesome idea. Needs to happen	Agreed.	I've always liked this one.
1324	Show Secondary Sequences in Tooltip	Graphical Client	2.3.13	Improvement	New	John	NodeStyles	ASAP	Awesome feature. There are no other visual queues for secondary sequences.	John can do this...	Understand the issue. This is just to show that at least one secondary sequence exists. TODO, ask what are secondary sequences are useful for.
1829	Shade Duplicate Jobs/Nodes Differently	Graphical Client	2.4.5	Improvement	New	John	NodeStyles	Soon	Very useful.	John can do this...	I like this one too. But not sure that best solution is.
1846	Long node names are illegible	Graphical Client	2.4.5	Annoyance	New	John	NodeStyles	Soon	Not a bad thing to have in there. Not sure how much work it would be.	Not sure I like the proposed solution, but its a John UI thing if it is to be done.	Not sure what the best solution will be for this.
1001	Hide Node Labels if Unreadable	Graphical Client	2.1.9	Improvement	New	John	NodeStyles	Defer	Does anyone really care?	Performance. John can do this...	Understand the issue.

1830	Collapse Duplicate Children	Graphical Client	2.4.5	Feature Request	New	John	JobStyles	Soon	Not sure what Red Vision wants with this since they never replied	Should do this. Its a good idea regardless.	Not getting this one. Will review again later.
1363	No association between job groups/details and queue servers	Graphical Client	2.3.13	Improvement	Active	John	JobNavigation	Soon	Don't think we need this.	I disagree. I like this idea, but its fairly low priority.	Not getting this one. Will review again later.

1328	Collapsable Node Regions	Graphical Client	2.3.13	Improvement	New	John	-	Soon	Jim thinks this is useful	Very.	I like this one too.
1327	Dialogs do not appear over the correct Parent frame	Graphical Client	2.3.13	Annoyance	Active	John	-	Soon	Not necessary, but it gets really annoying and customers keep bitching	Agreed.	Understand the issue.
1210	Multi-file select in MRayAddTextures	Plugins	2.3.5	Improvement	New	John	-	Soon	A little more work	I think this requires changing the underlying API classes, so its better suited to John.	Think I understand the issue.
1429	Plugin Autobuilding	General	2.4.1	Feature Request	New	John	-	Soon	Great idea.	Agreed.	I like this one too.
1840	Job Output Indicators	Graphical Client	2.4.5	Feature Request	New	John	-	Soon	Fairly easy to do, makes RV happy.	Agreed.	Another handy feature.
1349	Avoid editor religious wars...	General	2.3.13	Improvement	New	John	-	Soon	It would be great, but I don't have the time.	Sounds like something for John.	I like this one too.
1404	Clientside Job Manager Stats Caching	Graphical Client	2.3.15	Annoyance	New	John	-	Soon	Wrong, but so what.	Minor UI bug, but should be fixed.	Understand the issue.
1842	Node Viewer collapse/expand status after linking	Graphical Client	2.4.5	Improvement	New	John	-	Soon	Seems easy enough	John can do this...	Sounds handy.
1437	Complex BuilderParam UI	Node Builders	2.4.1	Improvement	New	John	-	Soon	Because I'm never going to do it.	John can do this...	Sounds handy.
1857	Access to full node right-click context menu from browser	Graphical Client	2.4.5	Improvement	New	John	-	Soon	The limited subset we talked about = good. Everything else is bad.	Agreed.	Think I understand the issue.
1512	Plugin Javadocs Button	Graphical Client	2.4.1	Feature Request	New	John	-	Soon	Would be cool, but isn't at all necessary	I disagree. This is sorely lacking!	Does Java have a HTML renderer?
968	State Based Node/Job Expansion and Framing	Graphical Client	2.1.9	Feature Request	New	John	-	Soon	Jim thinks it is great	Absolutely!	Sounds handy.
1913	Managing secondary file sequences	Graphical Client	2.4.6	Improvement	New	John	-	Soon	Good ideas. We should do it.	John can do this...	Think I understand the issue.
338	Owner|View Pulldown Menu	Graphical Client	1.9.12	Feature Request	Defer	John	-	Defer	The ability to surf working areas using the right-click menu on nodes makes this pretty much obsolete	Mostly agree, but I still see some utility.
1301	Pipeline instant messanger	General	2.3.11	Feature Request	New	John	-	Defer	Awesome feature. Huge bang for buck.	Complicated and time consuming... Not the highest priority at the moment.
1402	Two new Dispatcher Related Panels	Java API	2.3.15	Feature Request	New	John/Jesse/Jim	Queue	Soon	While these are good ideas, the contents of the panels will change once we overhaul the dispatcher in the new Queue. So I'll deal with these then.	I'd like this done sooner if time allows since it would help explain how the queue currently works until it works a different way.	This sounds very handy to have.
1024	Windows Networking Exception	Server Daemons	2.2.1	Annoyance	New	John/Jim	WinJobMgr	Soon	Looks like Sven did the hard work for this one.	Not exactly... Still unresolved. John has been investigating.	This needs to be a part of reviewing all the networking code.
548	View Version Trees	Graphical Client	2.0.3	Feature Request	Active	John/Jim	-	Soon	Can't believe more people don't ask for this.	Agreed. Needs some backend support still I think to get checked-in trees in one API call.	I like this one too.

1524	Dummy file/scene option when registering nodes	General	2.4.1	Feature Request	Active	Wen	EditorParams	Trivial	Honestly, this isn't really necessary at all, but would be fairly easy to implement when Editor Params are done.	Don't need parameters for this, could just add the functionality to the current Maya editors easily.
594	ZBrush Plugins	Plugins	2.0.8	Feature Request	New	Wen	-	Test	We should at least have some one look at automation with Zbrush. Though it looks like the made it even worse in 3.0	Yeah, no idea about the current state of affairs.
1849	MayaBuildAction should use -defaultNamespace	Plugins	2.4.5	Improvement	New	Wen	-	Trivial	Easy fix.	Agreed.
482	More Mac OS X Editor Plugins	Plugins	2.0.15	Feature Request	Defer	Wen	-	Trivial	Should be fairly easy to implement.	Agreed.
1899	MayaNoRef 2.4.1 does not work on windows	Plugins	2.4.6	Defect	New	Wen	-	Trivial	Easy fix	Agreed.
1826	Relative Thumbnail ImageNumber	Plugins	2.4.5	Improvement	New	Wen	-	Trivial	Easy to do.	Agreed.
1330	Add a JEdit editor	Plugins	2.3.13	Feature Request	New	Wen	-	Trivial	Easy enough.	Agreed.
1851	MayaExport doesn't export set contents if includeSet is true	Plugins	2.4.5	Defect	New	Wen	-	Trivial	Maya fixed a bug we were taking advantage of.	Agreed.
1414	Support for Adobe CS3	Plugins	2.3.15	Feature Request	New	Wen	-	Trivial	And CS4. fucking adobe.	Agreed.
1653	Add Optional Units/FrameRange to MayaMEL	Plugins	2.4.3	Improvement	New	Wen	-	Soon	Jesse's Solution wins	Uncle
1725	Comp actions can kill a fileserver	Plugins	2.4.3	Improvement	New	Wen	-	Soon	This is really hot and the copy frame idea should be a generic part of the CommonActionUtils. Can see many uses for this.	Agreed.
1763	Splice Action RFE - automatic start/length source parms	Plugins	2.4.4	Improvement	New	Wen	-	Soon		Agreed.
1483	Maxon's Cinema 4D Editor and Render Actions	General	2.4.1	Plugins	New	Wen	-	Defer	Do we really care about Cinema4D?	Not now.
1191	Support Maya Lightmap Renderer	Plugins	2.3.5	Improvement	Defer	Wen	-	Defer	Needs Node Directories?	Agreed.
157	Fcheck Viewer only works with IFF files	Graphical Client	1.8.4	Annoyance	Defer	-	-	On Hold	Autodesk broke it	Should test this again and see if there are any improvements or alternatives.
917	SyflexApplyCache SourceParams Override	Plugins	2.1.7	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
522	ShakeSync Tool	Plugins	2.0.0	Feature Request	Active	Wen	-	On Hold	No one seems to care.	I disagree about it being unneeded, but there isn't high demand either.
1420	NukeDebugTexture Action	Plugins	2.3.15	Feature Request	New	Wen	-	On Hold	Not necessary.	I disagree about it being unneeded, but there isn't high demand either.
1681	Redesign data structure visibility in BaseStage	Node Builders	2.4.3	Improvement	New	Jesse	-	On Hold	If it ain't broke . . .	Next time you are in there for something else, otherwise it can wait.
692	Node Files Panel Limit	Graphical Client	2.0.16	Defect	Active	John	-	On Hold	Yeah it's broken, but haven't noticed anyone complaining	Agreed. At some point we should overhaul the whole damn thing and make it all OpenGL, but not now.
1329	Quadrant Node Look	Graphical Client	2.3.13	Improvement	New	John	-	On Hold	Do it after Custom Node Styles is done	Not sure this makes sense now that we have per-Link states.
1586	Job Killing Signals	Server Daemons	2.4.2	Improvement	New	Jim	-	On Hold	Until we have to support a studio using software that really needs this	Agreed.
1089	Adobe After Effects Support for Mac OS X and Windows XP	Plugins	2.2.5	Improvement	Active	Jesse	-	On Hold	Because I don't want to write more After Effects Javascript.	Agreed.
1600	AfterFXRender does not respect comp Start name	Plugins	2.4.2	Defect	New	Jesse	-	On Hold	Who uses afterfx these days?	Agreed. Until someone asks for it...
992	Organic Node Layouts	Graphical Client	2.1.9	Feature Request	New	John	-	On Hold	Can be done as part of CustomNodeStyles	Hard to do well and not the most important right now.
1003	Type Filtering in the Node History Panel	Graphical Client	2.1.9	Improvement	New	Jim	Branching	On Hold	Whenever we get a chance	Even less interested in this.
685	Listing of New Versions	Scripting Client	2.0.14	Feature Request	Active	Jim	SQL	On Hold	Doesn't seem much need for this.	Agreed. When we move the event stuff over to an SQL database, it won't matter.
1615	Windows machines not finding Jython Cache	General	2.4.2	Feature Request	Active	Jim	PLPYTHON	On Hold	Since no one is using windows and jython (and hopefully never will)	MLB is on the horizon.
122	Job Viewer Display Bug	Graphical Client	1.8.3	Annoyance	Defer	John	-	On Hold	Don't hit spacebar so fast.	Agreed.
940	Distributed File Manager	Server Daemons	2.1.8	Feature Request	Active	Jim	-	On Hold	Given what we have discovered, are we really going to get better performance out of this? Mark's feature would give us almost the same benefits without any messiness. And the NFS feature makes this essentially irrelevant.	Agreed.
1004	Change to Node History display of Check-in Messages	Graphical Client	2.1.9	Improvement	Active	Jim	Branching	On Hold	Whenever we get a chance	Even less interested in this.
567	Liquid/Pixie Plugins	Plugins	2.0.5	Feature Request	New	Jim	-	On Hold	No customers.	Agreed.
1019	Port Houdini Action Plugins to Windows	Plugins	2.1.9	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
1569	Support for plremote to be a Protocal Handler	General	2.4.1	Improvement	Defer	Jim	-	On Hold	Do we care?	Nope.
1587	Gelato 2.2R1 Support	Plugins	2.4.2	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
1030	Digital Fusion Plugins	Plugins	2.2.1	Feature Request	New	-	-	On Hold	Please god no.	Agreed. Until someone asks for it...
583	Job Spreadsheet Panel	Graphical Client	2.0.7	Feature Request	Defer	-	JobNavigation	On Hold	See a lot of overlap with 1834. We should just considering merging the features into one panel	I disagree. Very different purpose, but maybe overlaps somewhat with other ideas Ant has about render wrangler UI improvements.
287	Finish Porting CoordSys/Matrix Classes	Java API	1.9.4	Feature Request	Defer	Jim	-	On Hold	Because we haven't missed it yet.	Agreed.
593	Turtle Plugins	Plugins	2.0.8	Feature Request	New	-	-	On Hold	No customers.	Agreed. Until someone asks for it...
1022	Port Gelato Action Plugins to Windows	Plugins	2.1.9	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
1163	Ultraedit studio editor	Plugins	2.3.4	Feature Request	New	-	-	On Hold	Do we care?	Agreed. Until someone asks for it...
534	RealFlow Plugins	Plugins	2.0.1	Feature Request	Defer	-	-	On Hold	Do we care?	Agreed. Until someone asks for it...
1021	Port PRMan Action Plugins to Windows	Plugins	2.1.9	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
415	HdrGen Action Plugin	Plugins	1.9.19	Feature Request	Defer	-	-	On Hold	Do we care?	Agreed. Until someone asks for it...
532	Maxwell Plugins	Plugins	2.0.1	Feature Request	Defer	-	-	On Hold	Do we care?	Agreed. Until someone asks for it...
700	Secondary Queue Managers	Server Daemons	2.0.17	Feature Request	New	Jim	-	On Hold	No demonstrable need for this feature	Maybe at Disney. Not sure how it would work though because something still needs to dispatch the jobs centrally..
424	MASSIVE Plugins	Plugins	1.9.19	Feature Request	Defer	-	-	On Hold	Do we care?	Agreed. Until someone asks for it...
1564	Java Annotations for Network Messaging	Java API	2.4.1	Improvement	New	Jim	-	On Hold	This would be awesome, but seems like a lot of work. Might be something better given to John to play with for a while?	Great idea, but doesn't change anything functionally. Maybe do it as part of Pipeline3?
964	Column Style Node Browser	Graphical Client	2.1.9	Improvement	New	Jim	-	On Hold	I see no reason for Mac shit in Pipeline.	Not a high priority, but I like this particular Mac shit.
601	IvView Editor on Windows & Mac OS X	Plugins	2.0.9	Improvement	New	Wen	-	On Hold	If we really want this feature	No demand.
1406	Toolset Setup Wizard	Plugins	2.3.15	Feature Request	New	Wen	-	On Hold	This would be huge.	I like the idea, but it really only saves the Pipeline Consultant time and not the customer since its only used once per studio. Not a high priority.
1023	Port Syflex Action Plugins to Windows	Plugins	2.1.9	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
1456	Selective Node Bundle Unpack	General	2.3.15	Improvement	New	Jim	-	On Hold	It would be nice, but seriously, who needs it?	Agreed.
1376	Extend plremote(1) to Handle Generic Jython	Graphical Client	2.3.13	Feature Request	Active	Jim	-	On Hold	Does anyone still care?	I think it would be cool, but no idea how to handle the security problems.
702	Deep Repository	General	2.0.17	Feature Request	New	Jim	-	On Hold	No one currently wants it. And implementation is problematic.	Not sure it is possible. Weta wanted this originally. I can possibly see some future demand for something like this from big studios.
598	Windows Specific Air Editor Plugins	Plugins	2.0.8	Feature Request	New	-	-	On Hold	No customers.	Agreed. Until someone asks for it...
1020	Port AIR Action Plugins to Windows	Plugins	2.1.9	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
196	Free Swap Space	Graphical Client	1.8.8	Feature Request	Defer	Jim	-	On Hold	We've survived for ages without this.	Agreed, not sure we ever need to do it.
1133	AfterFX Editor on Mac OS X	Plugins	2.3.2	Improvement	New	-	-	On Hold	Does anyone really care?	Agreed. Until someone asks for it...
1171	Unfold3D editor plugin	Plugins	2.3.5	Feature Request	New	-	-	On Hold	Do we care?	Agreed. Until someone asks for it...
611	XSI Plugins	Plugins	2.0.8	Feature Request	New	-	-	On Hold	No customers using XSI	Agreed. Until someone asks for it...

## Sheet3
Defect	Orange 3
Feature Request	Turquoise 4
Annoyance	Orange 4